## Signature Page
¦ | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
| Client | [6 empty] | List
| Plant | [6 empty] | Document Register
Location
| Client Document Number | [16 empty] | Standard-0-LST-0001-1-R0
| Rev: | Date: |  |  | Status: | [7 empty] | Prepared By: |  |  |  | Checked By: |  |  |  | Approved By:
Signature Page

## Document Register
¦
Client
| Plant |  |  |  | Document Register |  |  |  | Standard-0-LST-0001-1-R0
| Location | [7 empty] | Client Document Number
| Document Number | [5 empty] | As | WBS | Qty
| Area | Type | Number | Codelco dwg # | Title | Remarks | Built | Area | Dwgs
| 0 |  | 0xxx |  | 0-0 Documentation
| 0 | LST | 0001 | 00 LST 0 01 528 | Document Register |  |  |  | 1
|  |  | 2xxx |  | 0-2 Project Administration
| 0 | PRC | 2003 | 70 SPC 0 12 72 | Project Execution Plan |  |  |  | 1
|  |  | 3xxx |  | 0-3 Planning
| 0 | DAT | 3001 |  | Project Schedule |  |  |  | 1
| 1 |  |  |  | 1 - Process Technology
| 1 | CAL | XXXX | 1-CAL-6510 | Process Calcualtions |  |  |  | 1
| 4 |  |  |  | 4 - Equipment
| 4 | CAL | XXXX | 4-CAL-0001 | Pump Calculations |  |  |  | 1
| 4 | DST | XXXX | 4-DST-XXXX | Pump Data Sheets |  |  |  | 1
| 4 | SPC | 0002 | 4-SPC-0002 | Horizontal Centrifugal Pumps |  |  |  | 1
| 4 | TAB | XXXX | 00 SPC 4 01 60 | Equipment Bid Tabulations |  |  |  | 1
[5 empty] | TOTAL DOCUMENTS |  |  |  | 8

## Commentary - Delete for Project
Document Register |  | Standard-0-LST-0001-1-R0
Commentary
The Document Register is a key planning and control document to record all documents that
will be produced on a project. It will be developed as part of project planning and will be
maintained throughout the project by the respective disciplines.
The document register is the primary document for assigning and recording of document
numbers and titles.
Project information will be filled in on the "Signature Page" only. It will automatically be copied to
the header on the "Document Register" sheet.
File types and there allocation within work areas is defined in 0-PRC-0003: File Structure
"WBS Area" is the work break down area for drawings that are associated with a physical
area in the plant.
"Qty Dwgs" is the number of drawings that are expected. This is used to idintify the total
number of documents (deliverables) required for a project.
"Document Status" is used to track document completion based on the PEM status
levels for progress measurement. When documents are published, there status level
must be updated in this register.
"Subcontract Documents" columns are used to track which documents are required as part
of construction contracts. They can be used for planning purposes and for extracting
the relevant documents out of this list to prepare the subcontract document list. These columns
are not part of the formal published document register.