# 0-LST-0001 — Document Register

## 1.0 Document Information

| Field | Value |
| --- | --- |
| Project | MEG Transfer Pump Skid |
| Client | B Star Chemetics |
| Location | Sarnia, Ontario, Canada |
| Document ID | 0-LST-0001 |
| Document Title | Document Register |
| Document Type | LST (Documentation) |
| Due Date | 2026-03-14 |
| Project End Date | 2026-08-01 |
| Risk Flags Active | None |

## 2.0 Revision History

| Rev. | Date | Status | Prepared By | Checked By | Approved By | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| 0.0 | 2024-01-23 | Issued for Review | Project Manager | Lead Engineer | Client PM | Initial Issue for Project Planning Review |

## 3.0 Purpose

The Document Register is a key planning and control document to record all documents that will be produced on a project. It is developed as part of project planning and maintained throughout the project by the respective disciplines. This register ensures that all required deliverables are identified, assigned, and tracked against their due dates, facilitating effective project execution and control.

## 4.0 Project Data Summary

| Field | Value |
| --- | --- |
| Equipment | horizontal centrifugal pump |
| Fluid | Monoethylene Glycol (MEG), 95% by weight |
| Flow | 45 m³/h |
| Pressure | 10 bar |
| Temp | 65 °C |

## 5.0 Document Register

The following table lists all planned deliverables for the MEG Transfer Pump Skid project, including their unique identifiers, titles, responsible disciplines, and target due dates.

| Document ID | Type | Title | Responsible Discipline | Due Date | Status |
| --- | --- | --- | --- | --- | --- |
| 0-LST-0001 | LST | Document Register | PM | 2026-03-14 | Issued |
| 0-PRC-2003 | PRC | Project Execution Plan | PM | 2026-03-28 | Planned |
| 0-DAT-3001.0 | DAT | Project Schedule | PM | 2026-03-28 | Planned |
| 1-PRC-0001 | PRC | Process Design Criteria | Process Engineer | 2026-06-20 | Planned |
| 1-CAL-XXXX | CAL | Process Calculations | Process Engineer | 2026-05-09 | Planned |
| 4-PRC-0007 | PRC | Pump Calculation Procedure | Mechanical Engineer | 2026-04-25 | Planned |
| 4-CAL-0001 | CAL | Pump Calculations | Mechanical Engineer | 2026-07-11 | Planned |
| 4-DST-XXXX | DST | Pump Data Sheets | Mechanical Engineer | 2026-06-06 | Planned |
| 4-SPC-0002 | SPC | Horizontal Centrifugal Pumps | Mechanical Engineer | 2026-07-18 | Planned |
| 4-SPC-0001 | SPC | General Equipment Requirements | Mechanical Engineer | 2026-06-20 | Planned |
| 4-TAB-XXXX | TAB | Equipment Bid Tabulations | Mechanical Engineer | 2026-07-25 | Planned |